## Risk Register
Risk ID | Domain | Risk Event | Cause / Driver | Potential Consequence | Inherent Likelihood | Inherent Impact | Inherent Score | Inherent Rating | Accountable Owner | Current Controls / Position | Treatment Action | Target Likelihood | Target Impact | Target Score | Target Rating | Status | Target Date / Gate | Evidence Required
AI-R-001 | Fairness | Candidate ranking systematically disadvantages one or more groups | Unrepresentative data, historical hiring patterns, unsuitable features or proxy variables | Qualified applicants receive fewer opportunities; discrimination, legal and reputational harm | 4 | 5 | 20 | Critical | CHRO / Recruitment Lead | None evidenced at assessment stage | Representative dataset review; feature and proxy analysis; subgroup outcome tests; approved thresholds; remediation and periodic monitoring | 2 | 4 | 8 | Medium | Open | Before pilot approval | Fairness tests, approvals and remediation log
AI-R-002 | Accuracy & Validity | CV details are extracted or scored incorrectly | Parsing errors, weak job-related criteria, inadequate validation or model limitations | Qualified applicants are wrongly deprioritised; recruitment quality declines | 4 | 4 | 16 | High | Model Risk / Analytics Lead | Human review is planned but not yet designed | Job analysis; benchmark validation; error analysis; confidence flags; correction route; periodic sampling | 2 | 3 | 6 | Medium | Open | Before pilot approval | Validation report and error log
AI-R-003 | Human Oversight | Recruiters over-rely on AI scores or rankings | Automation bias, poor training, unclear authority or rushed workflows | AI output becomes a de facto decision; errors and bias are not challenged | 4 | 5 | 20 | Critical | Recruitment Lead | Final decision is assigned to a human recruiter | Oversight SOP; independent review prompts; override and stop-use authority; training; override monitoring | 2 | 4 | 8 | Medium | Open | Before pilot approval | SOP, training, override logs
AI-R-004 | Privacy | Applicant data is used, retained or shared beyond necessity | Excessive collection, unclear purpose, vendor reuse, weak retention or cross-border arrangements | Privacy intrusion, complaints, sanctions and loss of trust | 4 | 5 | 20 | Critical | Privacy Officer | Standard recruitment privacy process to be confirmed | Privacy assessment; purpose limitation; minimisation; retention and deletion; access controls; vendor data restrictions | 2 | 4 | 8 | Medium | Open | Before contracting | Privacy assessment and retention evidence
AI-R-005 | Transparency | Applicants or reviewers do not understand AI use, limitations or rationale | Inadequate notice, weak explanations or unavailable reason information | Reduced ability to question outcomes; complaints and low trust | 4 | 4 | 16 | High | HR Legal Lead | None evidenced | Candidate notice; reviewer instructions; reason information; limitations; contact and human-reconsideration route | 2 | 3 | 6 | Medium | Open | Before pilot approval | Notice, instructions and complaint process
AI-R-006 | Accessibility & Inclusion | System design disadvantages non-standard CVs or applicant circumstances | Language variation, disability, career breaks, formatting differences or inaccessible submission paths | Certain applicants face unequal access or incorrect assessment | 3 | 5 | 15 | High | Recruitment Lead | Alternative route not yet confirmed | Accessibility testing; inclusive design review; alternative submission and accommodation; outcome monitoring | 2 | 4 | 8 | Medium | Open | Before pilot approval | Accessibility test and accommodation procedure
AI-R-007 | Security & Resilience | Candidate data or system outputs are exposed, altered or manipulated | Weak access, integration flaws, insecure APIs, attack or poor incident response | Personal-data breach, corrupted ranking, service disruption and reputational harm | 3 | 5 | 15 | High | Information Security Lead | Enterprise controls to be confirmed | Security assessment; least privilege; encryption; logging; resilience testing; incident response; supplier security obligations | 2 | 4 | 8 | Medium | Open | Before integration | Security assessment and test results
AI-R-008 | Third Party | Vendor changes model, data, features or thresholds without adequate review | Weak contract, limited transparency, subcontractors or inadequate change notification | Performance and impact shift without approval; loss of control or auditability | 4 | 4 | 16 | High | Technology Owner / Procurement | Vendor not selected | Due diligence; contract controls; change notification; version records; audit evidence; revalidation and exit plan | 2 | 3 | 6 | Medium | Open | Before contracting | Due diligence, contract and change records
AI-R-009 | Governance & Accountability | Ownership, approvals or escalation responsibilities are unclear | Incomplete RACI, fragmented functions or absence of formal governance forum | Risks remain unresolved; incidents and complaints are mishandled | 3 | 4 | 12 | High | AI Governance Lead | Use case and impact records identify proposed owners | Approved RACI; governance forum; risk acceptance authority; escalation and reassessment triggers | 2 | 3 | 6 | Medium | Open | Before pilot approval | RACI, decision record and minutes
AI-R-010 | Monitoring & Drift | Performance or group outcomes deteriorate after deployment | Population change, data drift, model update or changing labour market | Increasing errors or unequal outcomes remain undetected | 4 | 4 | 16 | High | AI Governance / Model Risk | No production monitoring exists | KPIs; subgroup outcomes; drift and override thresholds; review cadence; escalation and stop-use criteria | 2 | 3 | 6 | Medium | Open | Before production | Monitoring plan, dashboard and review records
AI-R-011 | Contestability | Applicants cannot correct data or obtain meaningful human reconsideration | No service owner, inaccessible complaint process or incomplete decision records | Unfair outcomes persist; affected people lack remedy | 3 | 5 | 15 | High | HR Operations / Legal | General recruitment contact route to be confirmed | Correction and complaint workflow; service levels; human reconsideration; decision and response records | 2 | 3 | 6 | Medium | Open | Before pilot approval | Workflow, case log and response records
AI-R-012 | Purpose & Scope | System is used beyond the approved recruitment-screening purpose | Function creep, user convenience, new features or inadequate access restrictions | Unassessed impacts and obligations; inappropriate employment decisions | 3 | 5 | 15 | High | CHRO / Technology Owner | Prohibited uses identified in registration | Approved intended and prohibited uses; access restrictions; change approval; audit logs and user training | 1 | 4 | 4 | Low | Open | Before pilot approval | Purpose statement, permissions and logs

## Reference
AI Risk Register ¦ Case Study 01
Purpose | Operational tracker for the risks identified from the AI Impact Assessment.
Use case | AI-enabled recruitment screening ¦ AI-UC-001
How to use | Update blue-font input fields, keep evidence links or references current, and review ratings whenever controls, data, model, vendor or purpose changes.
Scoring | Likelihood (1–5) × Impact (1–5). 1–5 Low, 6–11 Medium, 12–19 High, 20–25 Critical.
Important | All entries are synthetic and illustrative. Tailor them to the client’s approved methodology, risk appetite and evidence.
Public source | https://www.nist.gov/itl/ai-risk-management-framework

## Scoring Matrix
Impact → | 1 | 2 | 3 | 4 | 5
1 | 1 | 2 | 3 | 4 | 5
2 | 2 | 4 | 6 | 8 | 10
3 | 3 | 6 | 9 | 12 | 15
4 | 4 | 8 | 12 | 16 | 20
5 | 5 | 10 | 15 | 20 | 25
Likelihood: 1 Rare, 2 Unlikely, 3 Possible, 4 Likely, 5 Almost certain
Impact: 1 Insignificant, 2 Minor, 3 Moderate, 4 Major, 5 Severe

## Summary
Risk Dashboard
Metric | Value
Total risks | 12
Critical inherent | 3
High inherent | 9
Open risks | 12
Critical target | 0
High target | 0